## Sheet1
Requirement | Sub Requirement | Tasks (all tasks shall include unit testing before they are handed over for formal testing) | Status (To be done, Started, Coded,Unit Test complete, In Formal Test, Complete, In Rework) | Assigned To | Date Status Update | Number of Hours worked (add hours to total)
The user shall have ability to start the application via standard terminal or development interfaces. The game user interface shall appear once the application is started. |  | Design and build the user interface as shown in the user interface design documents. Presentation only. Functionality tasks are listed below Shall inlcude a start button, ships in port, grids,pllace ship button, fire button and exit button at a minimum. | Started
The user shall be able start a new game of Battleship via the user interface. |  | Build and Code a 'Start" button to begin the game It shall be a normal part of the user interface. The main user interface will appear or become active when the "Start" Button is clicked. The "Start" button shall comply with the user interface style. (See user interface designs for style and layout information) | Started
The user shall be able to place their own game pieces wholly within their own Allied grid via the user interface
| The user shall be able to place their game pieces in either a horizontal or vertical position. No diagonal placement is allowed. | The placeShips() method shall be coded along with any applicable unit tests following the requirement listed. | Started
| The user shall not be able to place ships in overlapping positions. | See directly above | Started
| The user shall not be able to place their ships outside their own grid or on or within the opponent’s grid. | See directly above | Started
| For version 1, the second user shall consist of the CPU of the computer. Placement of the second users game pieces shall be automated and follow the same rules listed above. | The placeShips() method shall be modified as necessary to be used for both Player 1 and Player 2 | Started
The user shall have the ability to guess the location of the opponent’s game pieces via the user interface. | The user shall have one guess per turn. All other guesses in a single turn shall be ignored by the user interface. | Design and implement a method of (automated)turn taking withni the game complying with the requirement listed to the left. An indication of the current player's turn shall be a part of the user interface. | Started
| The user shall only be able to guess locations within the opponent’s or Target grid via the user interface or via a textual interface tied to the opponent’s grid. All other actions outside the opponent’s grid or the alternative interface shall be ignored. | An event based method shall be implemented such the code shall react to a mouse-click within Player 2's grid (and no other location). The mouse-click shall selet a location as a guess of an opponent's ship. The actual gussing action shall occur when the "Fire" event is activated by clicking the "Fire"Button (see user interface mock-ups) | Started
| c. For version 1, the second user shall consist of the CPU of the computer. “Guesses” from this player shall be automated and follow the same rules and indications as for the first user. | A random location guessing method shall be implemented to select pseudo-random numbers with which the CPU can guess Player 1's ship locations. The automated guesses must remain within the confines of Player 1's grid. All other guesses shall be ignored. | Started
The user shall have the ability to determine whether their guess of the location of an opponent’s game piece was correct or incorrect. The indication shall be textual, graphical or both. |  | A method of updating the user interface shall be designed and implemented to indicate when either the event-based or random location based event occurs and whether the location chosen.guessed was correct/incorrect. The method chosen shall comply with the user interface mock-ups or similar documentation. | Started
The user shall have the ability to determine the number of both correct and incorrect guesses via the user interface. |  | A method to count the number of correct and incorrect guesses shall be implemented. A method in the user interface shall be implemented as an indicatin to the user of the count(s). | Started
The user shall have the ability to determine if they have guessed all of the locations covered by a game piece and have thus “sunk” or removed the game piece from the game via the user interface. |  | A method shall be implemented that tracks the number of hits per playing piece. A method which indicates to the user via the user interface when each hit has occurred along with a second method which indicates that all possible hits for each individual ship have occurred shall be implemented. | Started
The user shall have ability to determine if they have “sunk” all of the game pieces of their opponents and thus have won the game via the user interface. |  | Another method shall be implemented which keeps track of the number of playing pieice's locations which have been found (or alternatively a total count of possible hits) shall be implemented. The method shall further indicate via the user interface that all ships have been sunk and one player has won the game. | Started
The user shall have the ability to reset the game board, removing all indications of the previous game including game pieces and any indications of game play via the user interface. |  | A method to reset the user interface to the status at the start of a new game shall be implemeted. All ships shall be removed from the board and all indications of either correct or incorrect guesses as well as the count of each shall be reset to the initial state. (See user interface mock-ups for a visual indication of the state) | Not started
The user shall have the ability to exit or terminate the game at any time via the user interface. The user interface shall disappear at this time. |  | A method to interrupt game play and exit the application shall be implemeted. | In Formal Test
The user shall have a way to separately guess a location via the user interface without “firing” at that location. |  | See the task on Line 10 | Started
The application shall run on Windows 7+ standard desktop computer available on the marketplace as of December 2016. |  | The application shall be tested on a Windows 7+ standard desktop application | In Formal Test
For version 1, the user shall have a minimum of 5 game pieces of various sizes corresponding to the physical board game pieces. The Sizes include 2, 3 ,3, 4,and 5 grid locations. |  | Game pieces of size 2, 3,3,4,and 5 shall be designed and implemented. | Started
For Version 1, the game board from an individual user shall have a minimum size of 10 squares by 10 squares. |  | A game board of size 10 squares by 10 squares shall be implemented as part of the user interface.The size and shape of the grid should comply wth the user interface design documents. | Started
For version 1, the system shall indicate via the user interface, the result of the human player’s ‘guess’ in less than 0.5 seconds. |  | A performance test shall be implememted which ensures that this requirement is satisfied. | Not started
For version 1, the system shall indicate via the user interface the choice of the CPU player’s ‘guess’ within 2 seconds but not less than 0.5 seconds. (This is to allow the human user to process and understand where the guess has occurred.) |  | A performance test shall be implememted which ensures that this requirement is satisfied. | Not started
Indication (either valid or invalid) via the user interface of a player’s placement of a single ship shall be completed within 1 second. |  | A performance test shall be implememted which ensures that this requirement is satisfied. | Not started
Indication of reset of the board via the user interface after the completion of a game shall be completed within 1 second. |  | A performance test shall be implememted which ensures that this requirement is satisfied. | Not started
Quick Start Guide/User Interface Written |  |  | Not Started
Requirements Review |  |  | Completed
Design Review |  |  | Scheduled for 01/19/2017
Software Test Plan Review |  |  | Started
Risk Assessment |  |  | Completed
Set up Version Control | Github |  | Completed
Formal Development Schedule |  |  | Not started
Acceptance Testing |  |  | Not started
Defect Tracking |  |  | Started
Schedule tracking |  |  | Not started